## How to use
Electrical Equipment RFQ & Bid Scorecard
Get quotes you can compare, then score them the same way every time.
1. Fill in the RFQ sheet
Project details, the equipment list and your dates. Send it to every bidder with your specification and drawings.
2. Ask every bidder for the same things
The RFQ lists what each quote must state: price basis, lead time from approved drawings, tests, freight, warranty and exceptions. That is what makes quotes comparable.
3. Log questions on the Clarifications sheet
Send the same answer to every bidder so nobody gains an advantage, and note any impact on price or lead time.
4. Enter the quotes on the Bid Comparison sheet
Yellow cells are inputs. Price, lead time and warranty score automatically; give the other criteria a 1–5 score.
5. Check the weights
Weights must add up to 100%. Change them to suit the project: a schedule-critical job may weight lead time above price.
6. Read the result
Each bidder gets a weighted score out of 100 and a rank. Use it to support the decision, not replace judgement on technical risk.
Example data: three example bidders are filled in on the Bid Comparison sheet so you can see how scoring works. Overwrite or clear them before use.
This workbook is a decision aid. Check every quote against your specification, and follow your organization’s procurement policy.
Free resource from CANDRON Energy Inc. · providers of Canadian-made switchgear, switchboards and transformers · candron.com · +1 (647) 616-2595

## RFQ
Request for Quotation: Electrical Equipment
Send this sheet with your specification and drawings. Ask each bidder to answer every line in section C.
A · Project & contacts
Project name |  |  |  | Location (city, province)
Owner |  |  |  | Engineer of record
Your company |  |  |  | Contact name
Email |  |  |  | Phone
RFQ issue date |  |  |  | Quotes due
Required on-site date |  |  |  | Target energization date
B · Equipment scope
Item | Tag | Equipment type | Qty | Key ratings (V, A or kVA, kA, BIL) | Enclosure / location | Standards | Notes
1
2
3
4
5
6
7
8
C · Every quote must state
# | Item |  |  | Bidder’s answer
1 | Unit and total price, in CAD, taxes excluded
2 | Price validity (days) and any escalation clause (e.g. metals)
3 | Lead time in weeks, counted from approved drawings
4 | Submittal drawing turnaround after purchase order (weeks)
5 | Tests included: routine tests, factory acceptance test, witness option
6 | Freight and delivery terms, including offloading and site access
7 | Warranty period and when it starts (shipment or energization)
8 | Certification: CSA, cUL or field evaluation; utility approvals if needed
9 | Recommended spare parts and their prices
10 | Start-up, commissioning or field service support offered
11 | Country of manufacture and final assembly
12 | Payment terms
13 | Exceptions, deviations and clarifications to the specification
D · Attachments sent with this RFQ
☐ Single-line diagram
☐ Specification sections
☐ Layout / site drawings
☐ Utility or authority requirements
Free resource from CANDRON Energy Inc. · providers of Canadian-made switchgear, switchboards and transformers · candron.com · +1 (647) 616-2595

## Bid Comparison
Bid Comparison
Yellow cells are inputs. Price, lead time and warranty score automatically; give the rest a score from 1 to 5.
1 · Quote details
Quote detail |  |  | Bidder 1 | Bidder 2 | Bidder 3 | Bidder 4 | Bidder 5
Bidder |  |  | Bidder A (example) | Bidder B (example) | Bidder C (example)
Total price (CAD, before tax) |  |  | 412000 | 389000 | 445000
Lead time (weeks from approved drawings) |  |  | 38 | 56 | 30
Drawing turnaround (weeks) |  |  | 3 | 5 | 2
Warranty (months) |  |  | 24 | 18 | 24
Freight & offload included? (Y/N) |  |  | Y | N | Y
Witnessed FAT included? (Y/N) |  |  | Y | Y | Y
Number of exceptions to the spec |  |  | 2 | 5 | 1
Country of manufacture |  |  | Canada | Imported | Canada
Price validity (days) |  |  | 30 | 45 | 30
2 · Weighted scoring
Criterion | Weight | How it is scored | Score 1–5 · Bidder 1 | Score 1–5 · Bidder 2 | Score 1–5 · Bidder 3 | Score 1–5 · Bidder 4 | Score 1–5 · Bidder 5
Price | 35% | Lowest total price scores 5; others pro rata
Lead time | 25% | Shortest lead time scores 5; others pro rata
Technical compliance | 15% | 1–5: meets the specification with no technical deviations | 5 | 4 | 5
Exceptions & commercial terms | 10% | 1–5: fewer exceptions and clearer terms score higher | 4 | 3 | 5
Warranty & support | 5% | Longest warranty scores 5; others pro rata
Testing & documentation | 5% | 1–5: witnessed FAT, test reports, drawings and manuals included | 5 | 4 | 5
Supplier track record | 5% | 1–5: references, past performance, local service | 4 | 4 | 3
Weights total (must be 100%)
3 · Result
Weighted score (out of 100)
Rank
Notes on the decision
Free resource from CANDRON Energy Inc. · providers of Canadian-made switchgear, switchboards and transformers · candron.com · +1 (647) 616-2595

## Clarifications
Clarifications Log
Send every answer to every bidder. Note any change to price or lead time.
# | Bidder | Question | Date asked | Answer (sent to all bidders) | Date answered | Impact on price / lead time
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Free resource from CANDRON Energy Inc. · providers of Canadian-made switchgear, switchboards and transformers · candron.com · +1 (647) 616-2595